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ANNEXURE C
NEW HOMES BUILD TIME GUARANTEE (FROM SLAB DOWN TO PRACTICAL COMPLETION)
This Annexure forms part of the HIA Contract dated between ARMOUR DEVELOPMENTS WA (“Builder”) and (“Client”).
Area and Scope Restrictions:
This guarantee is only valid for projects located within a 50 km radius of Perth CBD in the Perth metro area, involving homes under 250m², and where the Contract Price is below $500,000. It excludes jobs that involve landscaping and plantation shutters or paved common driveways.
1. Guarantee of Construction Duration
The Builder guarantees that the construction works, commencing from the slab-down stage until practical completion, shall be substantially completed within TEN (10) months from the date of commencement of works as specified in the Contract.
2. Scope of Guarantee
This guarantee applies specifically to all construction works from the slab-down stage through to practical completion, including all trades and services required for the successful completion of the project, excluding projects involving landscaping & plantation shutters.
3. Commencement of Works
Construction shall commence on or before 6 MONTHS FROM PPA DATE, unless delays are caused by circumstances beyond the Builder’s control, including but not limited to inclement weather, supply chain disruptions, or variations approved by the Client.
4. Extension of Time
Any extensions of time granted due to circumstances beyond the Builder’s control shall be documented in writing and shall not be deemed a breach of this guarantee.
5. Penalties for Delay
Should the Builder fail to achieve practical completion within TEN (10) months of the commencement date, and such delay is not caused by circumstances beyond their control, the Builder shall pay the Client liquidated damages amounting to $400.00 per week, up to a maximum of 10 weeks.
6. Payment Conditions
If any stage claim payment is overdue by more than ten (10) working days from the invoice date, the Build Time Guarantee shall be voided.
7. Material Availability and Re-Selection
In the event that required materials become unavailable, the Builder shall provide the Owner with the closest possible alternative selection(s). The Owner shall have five (5) days from receipt of the re-selection proposal to confirm or reject the alternative(s). If the Owner exceeds this five (5) day period, the Build Time Guarantee shall be deemed void.
8. Exclusions
This guarantee does not apply to delays caused by: 
· Changes or variations requested by the Owner;
· Unforeseen site conditions;
· Force majeure events;
· Delays in approvals or permits;
· Trade shortages, provided the Builder has made reasonable efforts to procure materials.
· The Owner’s failure to provide, or delays in the provision of, essential site services including permanent or temporary power and water supply required for construction activities.

It does not include projects involving landscaping, plantation shutters, or paved common driveways.
9. Notification of Delays or Material Shortages
The Builder shall notify the Owner in writing of any potential delays or material shortages as soon as they become apparent, including reasons and estimated durations.


10. Dispute Resolution
Any disputes relating to this guarantee shall be resolved in accordance with the dispute resolution process outlined in the main Contract.
11. Miscellaneous
This guarantee is only valid within the Perth metro area, specifically within a 50 km radius of Perth CBD, and only applies to suitable projects as described. It is independent of the main Contract and does not affect either party’s rights or obligations unless explicitly stated. The guarantee shall be deemed void if any of the conditions herein are breached.
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